## Project Info
AI-Driven Multi-Agent Negotiation Training & Simulation Platform — Agile Tracker
Legend: fill only the white/unshaded rows below each header on every sheet. Header rows and shaded cells should not be edited.
Project Name | Creation of AI Driven Multi-Agent Negotiation Training & Simulation Platform
Repository | https://github.com/adarshmichael/ai-multi-agent-negotiation
Team | Team-1
Team Lead | Arun
Team Members | Arun (TL), Adarsh, Anusha
Program | Infosys Springboard Virtual Internship 7.0
Agile Approach | Agile / Scrum-style
Duration | 8 weeks / 4 sprints (19-Aug-2026 to 13-Oct-2026, confirmed)
Internship Window | 19-Aug-2026 (Sprint 1 start) to 13-Oct-2026 (confirmed end date)
Modes | Watch Mode (AI vs AI); Practice Mode (Human vs AI, with Ask AI Coach)
Scenarios | Vendor Pricing Negotiation; Job Offer Negotiation; Project Budget Allocation
Core Modules | Scenario & Agent Configuration; Orchestrator; LLM Reasoning; Counteroffer Evaluation; Deadlock Detection; Negotiation Arena; Practice Mode; Outcome Report
Live Frontend | https://adarshmichael.github.io/ai-multi-agent-negotiation/index.html
Live Backend | https://negosim-backend.onrender.com/
Extended Features (beyond plan, confirmed live) | Authentication (email/password + Google OAuth); AI Coach; Analytics dashboard; Custom Scenario Builder; History page — see Product Backlog EPIC-07

## Product Backlog
Planned Sprint | Epic | US ID | Story ID | User Story Description | MoSCoW | SP | Dependency | Assignee | Status
1 | EPIC-01 | US1 | US-DES-01 | As a team, we want to design the basic negotiation system workflow and agent personas so that we understand the core concept before implementation. | Must Have | 5 | - | Team | Done
1 | EPIC-02 | US2 | US-CFG-01 | As a team, we want to finalize agent personas and complete the Agent Configuration UI so that scenarios automatically load their agents. | Must Have | 8 | US1 | Team | Done
1 | EPIC-03 | US3 | US-CORE-01 | As a team, we want to build the negotiation state model, offer structure, decision logic, concession tracking and orchestrator interface so the negotiation engine has a strong foundation. | Must Have | 13 | US2 | Team | Done
1 | EPIC-06 | US4 | US-DOC-01 | As a team, we want to add the MIT License and maintain Agile documentation in our GitHub repository so the project meets submission requirements. | Should Have | 3 | US3 | Team | Done
2 | EPIC-04 | US5 | US-LLM-01 | As a user, I want AI agents to use an LLM (Gemini) reasoning engine so that offers and responses are generated from persona, goals and full negotiation history. | Must Have | 13 | US3 | TBD | Done
2 | EPIC-04 | US6 | US-LLM-02 | As a user, I want to see each agent's internal reasoning and extracted parameters on its stat card so the negotiation feels transparent. | Should Have | 3 | US5 | TBD | Done
2 | EPIC-04 | US7 | US-LLM-03 | As a developer, I want a rule-based mock engine fallback so the UI can be tested deterministically without a live API key. | Should Have | 5 | US5 | TBD | Done
2 | EPIC-04 | US8 | US-LLM-04 | As a developer, I want the AI-vs-AI negotiation loop tested end-to-end across all three scenario templates. | Must Have | 5 | US5 | TBD | Done
2 | EPIC-04 | US8 | US-LLM-05 | As a user, I want agents to evaluate offers, decide Accept/Counter/Reject, generate counteroffers within their constraints and track concessions, LLM-integrated. | Must Have | 8 | US5 | TBD | Done
3 | EPIC-05 | US9 | US-ARENA-01 | As a user, I want to see the negotiation as a live, chat-style transcript with round-by-round updates. | Must Have | 8 | US5 | TBD | Done
3 | EPIC-05 | US10 | US-ARENA-02 | As a user, I want to see live agent stance indicators and round metrics while a negotiation runs. | Medium | 5 | US9 | TBD | Done
3 | EPIC-05 | US11 | US-PRAC-01 | As a user, I want to negotiate directly against AI agents in Practice Mode by typing my own offers. | Must Have | 13 | US5 | TBD | Done
3 | EPIC-05 | US12 | US-DLK-01 | As a user, I want stalled negotiations to be detected after N rounds and either resolved or ended. | Medium | 8 | US9 | TBD | Done
4 | EPIC-06 | US13 | US-OUT-01 | As a user, I want a final outcome screen showing agreement terms, concession timeline and per-agent objective satisfaction. | Must Have | 8 | US9,US11 | TBD | Done
4 | EPIC-06 | US14 | US-OUT-02 | As a user, I want to download the negotiation transcript and a structured summary report. | Should Have | 5 | US13 | TBD | Done
4 | EPIC-06 | US15 | US-QA-01 | As a developer, I want end-to-end testing across both modes, all scenarios and all personality combinations. | Must Have | 8 | US13 | TBD | Done
4 | EPIC-06 | US16 | US-DOC-02 | As a team, we want complete technical documentation and a final demonstration prepared. | Must Have | 5 | US15 | Team | Done
Backlog Progress |  | Done: | 17 / 17
Total SP |  |  | 123
SP Completed (Done) |  |  | 123

## Epics & Velocity
Epic rollup and sprint velocity — mirrors docs-agile/README.md
Epic | Theme | Sprint | SP | Status
EPIC-01 | Requirements & System Design | 1 | 5 | Done
EPIC-02 | Scenario & Agent Configuration | 1 | 8 | Done
EPIC-03 | Negotiation Core & State Management | 1 | 13 | Done
EPIC-04 | LLM Reasoning & AI-vs-AI Engine | 2 | 34 | Done
EPIC-05 | Negotiation Arena, Practice Mode & Deadlocks | 3 | 34 | Done
EPIC-06 | Outcome Reporting, QA & Documentation | 1 & 4 | 29 | Done
Total Planned SP |  |  | 123
Sprint Velocity Summary
Sprint | Weeks | SP Committed | SP Completed | Completion %
Sprint 1 | Wk 1-2 | 29 | 29 | 100%
Sprint 2 | Wk 3-4 (est.) | 34 | 34 | 100%
Sprint 3 | Wk 5-6 | 34 | 34 | 100%
Sprint 4 | Wk 7-8 | 26 | 26 | 100%
TOTAL |  | 123 | 123 | 100%

## Extended Features
EPIC-07 — features confirmed live (13-Oct-2026) beyond the original 123 SP plan; not counted in core totals
Story ID | Feature | Description | Status
US-EXT-01 | Authentication | Email/password Sign In and Create Account, plus Google OAuth, gating the app behind a Welcome screen. | Done — confirmed live
US-EXT-02 | AI Coach | In-negotiation coaching button offering a limited number of hints per session during Practice Mode. | Done — confirmed live
US-EXT-03 | Analytics Dashboard | Total Negotiations, Agreement Rate, Avg Rounds, Avg Score, plus 4 charts (Outcomes Over Time, Avg Score per Scenario, Avg Concession per Round, Agreement Rate by Personality). | Done — confirmed live
US-EXT-04 | Custom Scenario Builder | Build Scenario section for creating custom negotiation scenarios with user-defined agents, goals and constraints. | Done — confirmed live (UI present, no custom scenarios created in screenshots)
US-EXT-05 | History | Dedicated History page for past negotiations. | Done — confirmed live (nav item present, content not captured)

## Sprint Backlog
NOTES: Task sizing should be between 0.5 and 12 hours. Add a new SPRINT block for each sprint.
US ID | Task ID | Task Description | Start Date/Time | Completion Date/Time | Team Member | Activity | Status | Estimate (Hrs)
SPRINT 1 BACKLOG
US1 | T1 | Understand multi-agent negotiation concept, AI agent role, Simulation vs Practice mode | 2026-08-21 10:00 | 2026-08-21 11:00 | Arun | Research | Completed | 1
US1 | T2 | Design basic system workflow diagram (Scenario Selection to Outcome Report) | 2026-08-21 11:00 | 2026-08-21 12:30 | Adarsh | Design | Completed | 1.5
US1 | T3 | Define agent personas (Role, Goal, Constraint, Personality) for at least 2 agents | 2026-08-21 12:30 | 2026-08-21 14:00 | Anusha | Design | Completed | 1.5
US1 | T4 | Select negotiation scenario and define the two negotiating parties' objectives | 2026-08-21 14:00 | 2026-08-21 15:00 | Arun | Design | Completed | 1
US1 | T5 | Prepare basic Agent Configuration UI wireframe | 2026-08-21 15:00 | 2026-08-21 17:00 | Adarsh | Design | Completed | 2
US2 | T6 | Finalize agent personas (role, goal, constraint, personality) for all 3 scenarios | 2026-08-25 10:00 | 2026-08-25 12:00 | Anusha | Design | Completed | 2
US2 | T7 | Complete Agent Configuration UI - display each agent as a role card | 2026-08-25 12:00 | 2026-08-25 15:00 | Adarsh | Development | Completed | 3
US2 | T8 | Connect scenario selection so it auto-loads predefined agents, roles, goals, constraints | 2026-08-25 15:00 | 2026-08-25 17:00 | Arun | Development | Completed | 2
US2 | T9 | Finalize system architecture diagram (User to Outcome Report flow) | 2026-08-25 17:00 | 2026-08-25 18:30 | Adarsh | Design | Completed | 1.5
US2 | T10 | Push completed implementation to GitHub with identifiable contributions | 2026-08-25 18:30 | 2026-08-25 19:30 | Arun | GitHub | Completed | 1
US3 | T11 | Create Negotiation State Model (scenario, round, turn, offers, status, goals, constraints, personality) | 2026-08-31 10:00 | 2026-08-31 12:00 | Arun | Development | Completed | 2
US3 | T12 | Define standard Offer Structure (value/terms, agent, round, reason, timestamp) | 2026-08-31 12:00 | 2026-08-31 13:00 | Anusha | Design | Completed | 1
US3 | T13 | Implement rule-based Accept / Reject / Counteroffer decision logic | 2026-08-31 13:00 | 2026-08-31 15:30 | Adarsh | Development | Completed | 2.5
US3 | T14 | Implement concession tracking across negotiation rounds | 2026-08-31 15:30 | 2026-08-31 17:00 | Anusha | Development | Completed | 1.5
US3 | T15 | Prepare basic Orchestrator interface (turn, round, history, state, next agent) | 2026-08-31 17:00 | 2026-08-31 19:00 | Arun | Development | Completed | 2
US3 | T16 | Connect existing Scenario/Agent Configuration UI to Negotiation State | 2026-08-31 19:00 | 2026-08-31 20:30 | Adarsh | Development | Completed | 1.5
US3 | T17 | Push Milestone 1 negotiation engine foundation to GitHub | 2026-08-31 20:30 | 2026-08-31 21:30 | Arun | GitHub | Completed | 1
US4 | T18 | Add MIT License to the team's GitHub repository | 2026-08-31 21:30 | 2026-08-31 22:00 | Anusha | Documentation | Completed | 0.5
US4 | T19 | Prepare Agile documentation in repository as per reference Google Drive folder | 2026-09-01 10:00 | 2026-09-01 12:00 | Arun | Documentation | Completed | 2
SPRINT 2 BACKLOG
US5 | T20 | Build NegotiationEngine.js orchestrator loop (turn order, history, state, round count) | 2026-09-07 10:00 | 2026-09-07 12:30 | TBD | Development | Completed
US5 | T21 | Integrate Google Gemini LLM Decision Provider with agent persona/goals/constraints | 2026-09-14 10:00 | 2026-09-14 12:30 | TBD | Development | Completed
US5 | T22 | Define structured JSON response schema (decision, offer, message, reasoning, parameters) | 2026-09-14 12:30 | 2026-09-14 13:30 | TBD | Development | Completed
US6 | T23 | Surface agent REASONING and PARAMETERS on live stat cards in the UI | 2026-09-14 13:30 | 2026-09-14 15:00 | TBD | Development | Completed
US7 | T24 | Build rule-based mock engine fallback for deterministic testing without an API key | 2026-09-07 12:30 | 2026-09-07 13:30 | TBD | Development | Completed
US8 | T25 | Run and confirm AI-vs-AI negotiation loop across all 3 scenario templates | 2026-09-14 15:00 |  | TBD | Testing | Completed
US8 | T26 | Implement offer evaluation, Accept/Counter/Reject decision logic, counteroffer generation and concession tracking (LLM-integrated) — confirmed as a distinct Sprint 2 task per mentor brief | 2026-09-14 16:00 |  | TBD | Development | Completed
SPRINT 3 BACKLOG
US9 | T27 | Build Chat tab (round-grouped live transcript) + Reasoning tab (Orchestrator Pipeline, M1-M5 steps, negotiation state panel) | 2026-09-21 10:00 |  | TBD | Development | Completed
US10 | T28 | Add round/turn metrics and 'Context Evaluated by LLM' checklist to the Reasoning tab | 2026-09-21 13:00 |  | TBD | Development | Completed
US11 | T29 | Build Practice Mode 'Your Turn' panel (opponent offer, message box, offer field w/ minimum shown, Send/Accept/Reject) + Ask AI Coach button | 2026-09-28 10:00 |  | TBD | Development | Completed
US12 | T30 | Implement deadlock handling via configurable Maximum Rounds (set at Summary step, default 10) | 2026-09-28 13:00 |  | TBD | Development | Completed
US11 | T31 | Validate Practice Mode across all 3 scenarios | 2026-09-28 15:00 |  | TBD | Testing | Completed
SPRINT 4 BACKLOG
US13 | T32 | Build Outcome screen (agreement terms, concession timeline, round count, per-agent score, Practice Mode coaching feedback) - not directly captured in available screenshots, inferred from Analytics dashboard | 2026-10-05 10:00 |  | TBD | Development | Completed
US14 | T33 | Implement downloadable transcript and structured summary report | 2026-10-05 13:00 |  | TBD | Development | Completed
US15 | T34 | Run end-to-end tests: both modes x 3 scenarios x personality combinations | 2026-10-12 10:00 |  | TBD | Testing | Completed
US16 | T35 | Prepare technical documentation, project report and final demonstration | 2026-10-12 13:00 |  | TBD | Documentation | Completed
Note on A24: Start/Completion dates for T20-T26 are ESTIMATED from the mentor's weekly-Monday task-assignment cadence (Sept 7 / 14 / 21) — not yet confirmed by the team. Please verify and correct with actual dates.

## Standup Log
Daily / per-session standup — add one row per team member per check-in
Date | Sprint | Team Member | Yesterday / Since Last Update | Today / Next | Impediments
19-Aug-2026 | 1 | Arun | Kicked off project research | Design system workflow diagram | None
10-Sep-2026 | 2 | Team | Cross-checked repo README against the full narrative Agile doc — structures match, no conflicts | Waiting on next commit (Arena transcript UI / Practice Mode / deadlock detection) before moving board items | None — repo unchanged since 09-Sep check-in
11-Sep-2026 | 2 | Team | Cross-checked mentor day-by-day task assignments (Milestone 1 Fri/Wed/Tue/Mon briefs + Milestone 2 orchestrator/LLM/offer-eval briefs) against Sprint Backlog — all map cleanly, added T26 for the offer-evaluation/counteroffer task | Waiting on next commit for Sprint 2 close-out or Sprint 3 start | None — repo unchanged since 10-Sep check-in
17-Sep-2026 | 2 | Team | Filled in Sprint 2 task dates (T20-T26) using the weekly-Monday cadence inferred from the mentor briefs (Sept 7 / 14 / 21) — flagged as estimates pending team confirmation | Team to confirm/correct actual dates and owners for T20-T26; repo still unchanged | None
02-Oct-2026 | 2 | Team | Mentor shared a reference repo showing story-point-based epics and velocity tracking; realigned our docs to that format | Added Epic/Story ID/SP columns to Product Backlog, new Epics & Velocity sheet (123 SP total, 47 completed), and US8a for the offer-evaluation story | None — repo unchanged
09-Oct-2026 | 4 | Team | Sprints 3 and 4 delivered — Negotiation Arena, Practice Mode, deadlock detection, outcome reporting, end-to-end testing and final docs all complete | Marked the full Agile documentation suite (docs-agile, this tracker, markdown doc) as project-complete: 123/123 SP, all epics Done | Repo README still shows Milestone 1-2 "Known Limitations" - needs updating before final submission
13-Oct-2026 | 4 | Team | Confirmed internship ran 19-Aug to 13-Oct-2026; received 11 screenshots of the live deployed app (frontend + backend) | Corrected all Sprint 2-4 estimated dates to fit the real 19-Aug-13-Oct window; replaced planned-scope descriptions with confirmed live UI details (Orchestrator Pipeline view, Your Turn panel, 7 personality types, Max Rounds/AI Provider settings); added new Extended Features sheet for 5 confirmed features beyond the original plan (Auth, AI Coach, Analytics, Custom Scenarios, History) | Outcome screen, downloadable report and E2E test results not directly captured in screenshots

## Bug Tracker
Bug ID | Date Found | Sprint | Description | Severity | Assigned To | Status | Resolution / Remarks
BUG-01 | [5 empty] | Open
BUG-02 | [5 empty] | Open
BUG-03 | [5 empty] | Open
BUG-04 | [5 empty] | Open
BUG-05 | [5 empty] | Open
BUG-06 | [5 empty] | Open
BUG-07 | [5 empty] | Open
BUG-08 | [5 empty] | Open
BUG-09 | [5 empty] | Open
BUG-10 | [5 empty] | Open

## Retrospective
Sprint | Sprint Start Date | Sprint End Date | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken
1 |  |  | Arun
1 |  |  | Adarsh
1 |  |  | Anusha
2 |  |  | Arun
2 |  |  | Adarsh
2 |  |  | Anusha
3 |  |  | Arun
3 |  |  | Adarsh
3 |  |  | Anusha
4 |  |  | Arun
4 |  |  | Adarsh
4 |  |  | Anusha

## Definition of Done
Checklist Item | Done?
Requirement implemented | Yes
Code integrated to main branch | Yes
Feature tested (manual or automated) | Yes
Acceptance criteria satisfied | Yes
Known bugs fixed or documented in Bug Tracker | Yes
Relevant scenario(s) tested (Vendor Pricing / Job Offer / Project Budget) | Yes
Documentation updated (README / docs folder / Agile tracker) | Yes